UnityReach Global Volunteer Director

Complete Responsibilities: August 2026–January 3, 2029

Position purpose

The Volunteer Director is responsible for designing, managing, and supervising the complete volunteer lifecycle for the UnityReach Global 2028–2029 Cap-Haïtien Mission.

This lifecycle begins with volunteer recruitment and continues through:

- Registration

- Each One, Reach One referrals

- Application

- Screening

- Interviews

- Acceptance

- Department placement

- Payment coordination

- Documentation

- Training

- Readiness

- Deployment certification

- Travel

- Daily mission service

- Conduct management

- Volunteer care

- Recognition

- Final return and release

The Volunteer Director must build a system capable of managing 100–200 volunteers safely, fairly, efficiently, and consistently.

Mission profile

- Location: Cap-Haïtien, Haiti

- Departure: December 14, 2028

- Evangelistic Crusade: December 15–23, 2028

- Fellowship/Vacation: December 24, 2028–January 3, 2029

- Return: January 3, 2029

- Recruitment campaign: 50 + 50 = 100 volunteers

- Scalable capacity: 100–200 volunteers

Volunteer contribution

- Single volunteer: $3,995

- Married couple: $5,995

- Each child added: $1,995

Payment schedule:

- Deposit: December 2027

- 25% payment: February 2028

- 25% payment: April 2028

- Final payment: June 2028

The Volunteer Director communicates requirements but does not independently change prices, waive balances, collect money through personal accounts, or modify payment records.

Reporting relationship

The Volunteer Director reports to:

- Executive Director

- Deputy Executive Director

- Mission Director for mission operations

The Volunteer Director works closely with:

- Finance Director

- Logistics Director

- Safety & Security Director

- Medical Director

- Communications Director

- Administrative Coordinator

- Department Directors

- Department Coordinators

- Team Leaders

- Partnerships Director

- Safeguarding Lead

- Training administrators

- Haitian volunteer coordinators

Primary objectives

The Volunteer Director must:

- Recruit the appropriate number and mix of volunteers.

- Manage the Each One, Reach One campaign.

- Establish a fair application and acceptance process.

- Verify qualifications and required screening.

- Place volunteers in appropriate departments.

- Ensure every volunteer completes required documentation.

- Deliver the complete training and certification program.

- Monitor payment readiness with Finance.

- Maintain accurate volunteer records.

- Build the Team Leader structure.

- Prevent unqualified or unsafe deployment.

- Support volunteer communication and retention.

- Manage volunteer conduct and corrective action.

- Support volunteer health, welfare, and morale.

- Maintain daily accountability during deployment.

- Confirm every volunteer’s safe return and final release.

Authority

The Volunteer Director may:

- Develop volunteer policies

- Manage registration and applications

- Coordinate application reviews

- Recommend acceptance or rejection

- Approve routine volunteer assignments within delegated authority

- Assign required training

- Request background checks and documents

- Place volunteers on administrative or readiness hold

- Recommend reassignment

- Require corrective training

- Suspend someone from volunteer duty pending review

- Recommend removal from the mission

- Manage volunteer communications

- Establish Team Leader ratios

- Monitor readiness

- Approve volunteer-service recognition

- Control volunteer access to appropriate systems

- Close volunteer records after the mission

Limitations of authority

The Volunteer Director may not independently:

- Change participation prices

- Waive payments

- Issue refunds

- Handle money through personal accounts

- Guarantee acceptance

- Guarantee a particular department or leadership position

- Approve clinical practice

- Approve unverified professional credentials

- Override the Medical Director’s clinical decision

- Override a credible Safety hold

- Conceal safeguarding concerns

- Retaliate against a complainant

- Release confidential screening information

- Promise employment or compensation

- Add unregistered participants to the mission

- Permit someone to travel without deployment clearance

- Ignore Haitian law, immigration rules, or child-travel requirements

- Use recruitment totals to justify unsafe acceptance decisions

Volunteer Department structure

Recommended structure:

- Volunteer Director

- Deputy or Assistant Volunteer Director

- Volunteer Administrative Coordinator

- Recruitment Coordinator

- Each One, Reach One Coordinator

- Application and Screening Coordinator

- Interview Coordinator

- Background Check Coordinator

- Training and Certification Coordinator

- Department Placement Coordinator

- Volunteer Readiness Coordinator

- Volunteer Communications Coordinator

- Volunteer Care and Wellness Coordinator

- Family and Child Participant Coordinator

- Volunteer Conduct and Resolution Coordinator

- Recognition and Retention Coordinator

- Haitian Volunteer Coordinator

- Data and Reporting Coordinator

- Department Volunteer Liaisons

- Team Leaders

- Assistant Team Leaders

Volunteer categories

The system should distinguish between:

- Original volunteer

- Referred volunteer

- Individual volunteer

- Married-couple participant

- Child participant

- General volunteer

- Professional volunteer

- Clinical volunteer

- Ministry volunteer

- Technical volunteer

- Local Haitian volunteer

- Department Coordinator

- Team Leader

- Leadership volunteer

- Remote support volunteer

- Non-deploying volunteer

Each category may have different screening, training, payment, documentation, and assignment requirements.

Volunteer lifecycle

The official workflow is:

Interest → Registration → Application → Review → Interview if required → Accepted → Deposit Paid → Department Assigned → Screening Completed → Training Completed → Documents Verified → Payment Requirements Completed → Final Orientation → Certified for Deployment → Deployed → Mission Completed → Returned → Closed

Referral flow:

Volunteer Registers → Receives Referral Link → Invites Someone → New Person Registers → Application Reviewed → Accepted → Deposit Paid → Active Mission Participant

Phase 1: Volunteer-program foundation

August–December 2026

The Volunteer Director will:

- Meet with executive leadership.

- Review the Master Operations Handbook.

- Confirm the 100–200 volunteer planning range.

- Establish the Volunteer Department structure.

- Draft volunteer leadership job descriptions.

- Develop the Volunteer Management Plan.

- Create the volunteer application.

- Establish selection standards.

- Establish interview standards.

- Draft the Volunteer Code of Conduct.

- Coordinate safeguarding requirements.

- Establish background-check standards.

- Create the department-placement process.

- Develop the training framework.

- Establish volunteer data protections.

- Build the volunteer communication calendar.

- Prepare the preliminary Volunteer Department budget.

- Establish monthly reporting.

- Present a 90-day action plan.

Registration-opening preparation

Before October 1, 2026, confirm:

- Registration form

- Application form

- Mission information

- Contribution amounts

- Payment schedule

- Available roles

- Department descriptions

- Each One, Reach One system

- Referral code and link process

- Frequently asked questions

- Privacy notice

- Application acknowledgment

- Website workflow

- Confirmation messages

- Staff review process

- Application statuses

Phase 2: Registration and recruitment

October 2026–June 2027

Registration management

The Volunteer Director will monitor:

- Total registrations

- Completed applications

- Incomplete applications

- Original volunteers

- Referred volunteers

- Department interests

- Professional qualifications

- Language skills

- Family groups

- Geographic distribution

- Referral sources

- Withdrawals

- Duplicate registrations

Each One, Reach One campaign

Manage:

- Unique referral codes

- Personal referral links

- QR codes

- Referral dashboard

- Referral status

- Recruitment recognition

- Top recruiters

- Volunteers with no referral

- Campaign progress toward 100

- Referral privacy

- Anti-spam expectations

- Accuracy of volunteer invitations

Recognition levels:

- 1 referral: Mission Builder

- 2 referrals: Community Builder

- 3 referrals: Mission Ambassador

- 5 referrals: Recruitment Champion

- 10 or more: Global Impact Ambassador

Recognition does not guarantee:

- Application acceptance

- Leadership position

- Financial discount

- Free travel

- Department preference

- Special treatment

Recruitment strategy

Work with Communications to recruit:

- Physicians

- Nurses

- Dentists

- Vision professionals

- Pharmacists

- Pastors

- Bible workers

- Teachers

- Youth workers

- Children’s program volunteers

- Water professionals

- Logistics personnel

- Drivers

- Communications personnel

- Safety personnel

- Translators

- Administrative volunteers

- General relief volunteers

Recruit based on actual staffing gaps, not numbers alone.

Phase 3: Application review and preliminary placement

July–December 2027

Application review

Review:

- Identity

- Age

- Contact information

- Emergency contact

- Mission interest

- Department preference

- Experience

- Professional qualifications

- Language

- Availability

- Physical and functional considerations through protected procedures

- References when required

- Conduct disclosures

- Background-check requirements

- Family or child participation

- Agreement to policies

- Travel-document readiness

Application statuses

Use:

- Started

- Submitted

- Incomplete

- Under Review

- Additional Information Required

- Interview Required

- Provisionally Accepted

- Accepted

- Waitlisted

- Declined

- Withdrawn

- On Hold

- Cancelled

Interviews

Interviews may be required for:

- Leadership

- Clinical roles

- Child and youth roles

- Safety roles

- Financial roles

- Driving

- Technical water roles

- Ministry leadership

- Applicants with unclear qualifications

- Applicants with conduct or readiness concerns

Acceptance decisions

Acceptance should consider:

- Mission need

- Qualifications

- Conduct readiness

- Training commitment

- Travel readiness

- Capacity

- Department availability

- Housing

- Transportation

- Safety

- Ability to meet program requirements

Acceptance should not be based on:

- Friendship

- Family relationship

- Donation size

- Social status

- Church title alone

- Number of referrals

- Pressure from a partner

- Political influence

December 2027 deposit readiness

Coordinate with Finance to communicate:

- Deposit amount

- Deadline

- Approved payment method

- Confirmation process

- Payment-plan questions

- Late-payment procedures

- Withdrawal and refund policy

- Fraud-prevention instructions

The Volunteer Director should see necessary payment statuses but not unnecessary payment details.

Phase 4: Screening, assignments, and retention

January–June 2028

Screening

Coordinate:

- Identity verification

- References

- Background checks

- Professional-license verification

- Clinical credentialing

- Driving verification

- Child and youth clearance

- Ministry references

- Conflict-of-interest disclosures

- Code of Conduct acknowledgment

- Privacy acknowledgment

- Media acknowledgment

Professional approval belongs to the responsible qualified Director.

Department placement

Match volunteers based on:

- Mission need

- Qualifications

- Experience

- Language

- Training

- Physical capacity

- Accessibility needs

- Safeguarding clearance

- Leadership ability

- Schedule

- Local partnership requirements

Placement statuses

- Preference Submitted

- Under Review

- Provisionally Assigned

- Additional Qualification Required

- Assigned

- Reassigned

- Placement On Hold

- Removed from Department

Payment milestones

Coordinate volunteer-facing reminders for:

- February 2028 payment

- April 2028 payment

- June 2028 final payment

Refer waivers, payment arrangements, disputed transactions, and refunds to authorized Finance personnel.

Volunteer retention

Identify volunteers at risk of withdrawing because of:

- Financial difficulty

- Incomplete documents

- Training challenges

- Family concerns

- Travel concerns

- Unclear expectations

- Department dissatisfaction

- Lack of communication

- Health or accessibility concerns

- Conflict

Provide accurate information and appropriate referrals without making unauthorized promises.

Phase 5: Training and readiness preparation

July–September 2028

The Volunteer Director will ensure the training platform is operational.

Required core training

Every volunteer must complete:

- Welcome to UnityReach Global

- Mission Programs and Daily Operations

- Code of Conduct and Ethics

- Haitian Culture and Community Dignity

- Child and Vulnerable-Person Safeguarding

- Health, Wellness, and Personal Preparedness

- Safety, Security, and Emergency Response

- Teamwork and Conflict Resolution

- Humanitarian Service Standards

- Medical, Dental, Vision, and Medicine Boundaries

- Community Meals, Water, and Hygiene Safety

- Evangelism and Spiritual Care

- Communications, Media, and Data Privacy

- Travel, Housing, and Transportation

- Each One, Reach One Ambassador Training

- Department-Specific Training

- Final Readiness and Deployment Orientation

Training responsibilities

The Volunteer Director will:

- Assign required modules.

- Monitor progress.

- Monitor quiz scores.

- Manage retesting.

- Coordinate live training.

- Record attendance.

- Coordinate practical signoffs.

- Manage acknowledgments.

- Send reminders.

- Identify overdue volunteers.

- Coordinate multilingual access.

- Escalate repeated training failures.

- Prevent self-certification.

- Maintain audit history.

Phase 6: Final training and deployment certification

October–December 13, 2028

Readiness requirements

Confirm:

- Application accepted

- Deposit paid

- Required payment milestones complete or formally resolved

- Core training complete

- Department training complete

- Safeguarding complete

- Emergency drill complete

- Required acknowledgments signed

- Emergency contact complete

- Health and functional-readiness form complete

- Passport verified

- Background check complete when required

- Professional credentials verified when applicable

- Department assigned

- Team assigned

- Department approval

- Safety clearance

- Final orientation complete

- Final affirmation signed

Readiness statuses

- Not Ready

- Action Required

- Under Review

- Provisionally Ready

- Certified for Deployment

- On Hold

- Suspended

- Withdrawn

Certification review

The Volunteer Director must ensure:

- Automated requirements are complete.

- Department Director approves the assignment.

- Medical Director approves applicable clinical roles.

- Safety & Security clears deployment.

- Payment readiness is confirmed by Finance.

- Documents are verified.

- Final orientation is complete.

- Final review is documented.

- Authorized leadership approves certification.

The Volunteer Director must not approve someone merely to meet the numerical recruitment goal.

Team Leader system

The Volunteer Director will:

- Determine Team Leader needs.

- Recruit Team Leaders.

- Coordinate interviews.

- Verify training.

- Establish team sizes.

- Assign volunteers.

- Maintain team rosters.

- Train leaders in accountability.

- Monitor leader performance.

- Address leadership complaints.

- Replace unprepared leaders.

- Ensure every volunteer has a direct supervisor.

Recommended ratio:

- One Team Leader for approximately 8–12 volunteers

- Assistant Team Leaders for large or specialized teams

Volunteer communications

The Director should ensure volunteers receive:

- Application updates

- Acceptance decisions

- Payment reminders

- Training assignments

- Document reminders

- Department assignments

- Team assignments

- Travel instructions

- Housing information

- Packing list

- Safety information

- Final orientation information

- Departure instructions

- Mission updates

- Return instructions

Information must be available in:

- English

- Haitian Creole

- French

- Spanish where appropriate

Volunteer records

Maintain:

- Volunteer profile

- Application

- Referral attribution

- Acceptance decision

- Family grouping

- Department

- Team

- Role

- Emergency contact

- Documents

- Payment status

- Training

- Quiz attempts

- Acknowledgments

- Background-check status

- Credentials

- Attendance

- Practical signoffs

- Readiness

- Certification

- Conduct records

- Incident involvement

- Recognition

- Withdrawal or removal

- Final return status

Access must be restricted based on responsibility.

Departure day

December 14, 2028

Before arriving at FLL

The Volunteer Director will:

- Review the final deployment roster.

- Confirm every person is certified.

- Confirm no withdrawn or held person remains on the manifest.

- Confirm Team Leaders.

- Confirm department rosters.

- Confirm family groups.

- Confirm emergency contacts.

- Confirm communication channels.

- Review unresolved volunteer concerns.

At Fort Lauderdale airport

The Volunteer Director will:

- Arrive before volunteer check-in.

- Open the volunteer operations desk.

- Brief Volunteer Department personnel.

- Confirm each volunteer’s arrival.

- Coordinate with Team Leaders.

- Resolve roster issues.

- Refer passport and ticket problems to Logistics.

- Refer financial questions appropriately.

- Refer health concerns to Medical.

- Refer safety concerns to Safety.

- Address conduct problems.

- Confirm family and child accountability.

- Monitor missing volunteers.

- Confirm gate accountability.

- Confirm final boarding status.

No unapproved or uncertified person may be added at the airport.

Arrival in Cap-Haïtien

The Volunteer Director will:

- Confirm the total arrival count.

- Confirm Team Leader rosters.

- Coordinate vehicle groups.

- Confirm housing assignments.

- Address missing luggage affecting volunteer readiness.

- Conduct the arrival volunteer orientation.

- Review the Code of Conduct.

- Review curfew.

- Review reporting channels.

- Review emergency procedures.

- Confirm next-day reporting.

- Address immediate volunteer concerns.

- Report readiness problems to the Mission Director.

Daily mission operations

December 15–23, 2028

Morning responsibilities

The Volunteer Director will:

- Attend the leadership briefing.

- Receive department staffing updates.

- Review absences.

- Review volunteer health limitations using only necessary information.

- Review conduct concerns.

- Review transportation and housing accountability.

- Identify staffing shortages.

- Approve routine nonprofessional reassignments.

- Brief volunteer coordinators and Team Leaders.

During activities

The Volunteer Director will:

- Monitor volunteer attendance.

- Visit program sites.

- Support Team Leaders.

- Resolve routine volunteer concerns.

- Monitor conduct.

- Ensure appropriate breaks.

- Address fatigue.

- Coordinate reassignments.

- Receive complaints.

- Protect complainants from retaliation.

- Escalate medical, safeguarding, financial, or safety matters.

- Track volunteers removed from duty.

- Maintain accurate status records.

- Recognize strong performance.

- Keep the Mission Director informed.

Evening responsibilities

The Volunteer Director will:

- Confirm all teams returned.

- Review attendance.

- Review absences and illnesses.

- Review conduct concerns.

- Review volunteer complaints.

- Coordinate corrective actions.

- Update assignments.

- Prepare the next day’s staffing plan.

- Submit the daily Volunteer Department report.

- Coordinate volunteer announcements.

Volunteer accountability

The Volunteer Director must ensure accountability through:

- Morning attendance

- Team rosters

- Vehicle rosters

- Site check-in

- Site checkout

- Housing return

- Curfew confirmation

- Emergency headcounts

- Airport headcounts

- Final arrival confirmation

A volunteer should never be considered accounted for merely because someone assumes they are with another team.

Reassignment

Volunteers may be reassigned because of:

- Program needs

- Overstaffing

- Shortages

- Qualifications

- Language

- Health

- Accessibility

- Safety

- Conduct

- Transportation

- Site closure

- Fatigue

Clinical and technical reassignments require appropriate professional approval.

Volunteer conduct management

Minor concerns

Examples:

- First instance of lateness

- Dress-code misunderstanding

- Minor communication problem

- Failure to complete a routine task

Possible response:

- Private coaching

- Clarification

- Verbal reminder

- Written note

- Additional training

Significant concerns

Examples:

- Repeated insubordination

- Leaving the assigned site

- Unauthorized photography

- Repeated safety violations

- Harassment

- Impairment

- Unauthorized fundraising

- Serious conflict

- Misuse of supplies

Possible response:

- Written warning

- Reassignment

- Removal from duty

- Administrative hold

- Formal review

- Recommendation for removal

Immediate escalation

Immediately escalate:

- Child or vulnerable-person abuse

- Sexual exploitation

- Violence or threats

- Serious harassment

- Theft or fraud

- Unauthorized clinical practice

- Medication diversion

- Weapon concerns

- Major privacy breach

- Missing volunteer

- Criminal allegation

- Serious safety violation

The Volunteer Director should not independently investigate safeguarding or criminal allegations beyond securing immediate safety and documenting initial facts.

Volunteer complaints

Volunteers must have safe methods to report:

- Harassment

- Discrimination

- Bullying

- Unsafe assignments

- Leadership misconduct

- Retaliation

- Housing problems

- Transportation problems

- Privacy concerns

- Financial concerns

- Safeguarding concerns

- Health or accessibility barriers

Complaints should be:

- Acknowledged

- Categorized

- Protected

- Escalated appropriately

- Documented

- Addressed without retaliation

- Closed with appropriate follow-up

Volunteer health, wellness, and morale

The Volunteer Director will coordinate:

- Appropriate work-rest cycles

- Meal and hydration access

- Emotional-support referrals

- Conflict support

- Worship and reflection opportunities

- Reasonable accommodations

- Volunteer check-ins

- Recognition

- Team-building

- Fatigue monitoring

- Access to qualified medical care

The Volunteer Director does not diagnose or override medical decisions.

Recognition

Recognition may include:

- Service certificate

- Department acknowledgment

- Team recognition

- Each One, Reach One recognition

- Leadership recognition

- Volunteer spotlight with consent

- Appreciation event

- Post-mission letter

- Community-service-hour verification

Recognition must be fair and must not expose private information.

Volunteer fellowship and vacation period

December 24, 2028–January 2, 2029

The Volunteer Director remains fully responsible for:

- Volunteer accountability

- Code of Conduct enforcement

- Team Leader oversight

- Curfew monitoring

- Approved activity attendance

- Housing concerns

- Transportation accountability

- Volunteer health and wellness

- Conduct incidents

- Unauthorized travel prevention

- Family and child accountability

- Recognition and appreciation activities

- Department debriefings

- Volunteer evaluations

- Return-travel readiness

- Final roster confirmation

- Outstanding documentation

- Volunteer communications

The fellowship period is still part of the official mission.

Final day and return

January 3, 2029

Before leaving housing

The Volunteer Director will:

- Confirm the final volunteer roster.

- Confirm every volunteer is accounted for.

- Confirm family groups.

- Confirm Team Leaders.

- Confirm room checkout.

- Confirm keys and organizational property are returned.

- Review unresolved conduct, health, or travel concerns.

- Confirm vehicle assignments.

- Conduct the final volunteer briefing.

- Authorize movement with the Mission and Logistics Directors.

At Cap-Haïtien airport

The Volunteer Director will:

- Operate the volunteer-accountability desk.

- Confirm arrival at the airport.

- Coordinate Team Leader headcounts.

- Address missing volunteers.

- Coordinate family and child accountability.

- Refer documentation issues.

- Monitor gate accountability.

- Confirm boarding status.

- Maintain the official final passenger record.

During travel

The Volunteer Director will:

- Maintain volunteer accountability.

- Monitor welfare.

- Address conduct concerns.

- Support Team Leaders.

- Coordinate with Medical and Safety.

- Prepare volunteer-release procedures.

Upon arrival in Fort Lauderdale

The Volunteer Director will:

- Conduct the final volunteer headcount.

- Confirm children remain with parents or guardians.

- Confirm luggage and equipment responsibilities.

- Coordinate volunteer release.

- Record unresolved problems.

- Confirm no volunteer remains under mission supervision unintentionally.

- Notify leadership when all volunteers are released or assigned appropriate follow-up.

- Submit the final-day Volunteer Department report.

- Close active deployment records after authorization.

Required reports

The Volunteer Director must maintain:

- Monthly recruitment report

- Application report

- Each One, Reach One report

- Screening report

- Department-placement report

- Training-completion report

- Payment-readiness summary

- Documentation-readiness report

- Team Leader report

- Deployment-certification roster

- Daily attendance report

- Conduct report

- Complaint report

- Reassignment report

- Withdrawal report

- Recognition report

- Final volunteer closeout report

Performance indicators

Measure:

- Registrations

- Completed applications

- Acceptance rate

- Original volunteers

- Referred volunteers

- Referral conversion

- Professional roles filled

- Department staffing

- Training completion

- Quiz pass rates

- Document completion

- Payment readiness

- Background-check completion

- Credential verification

- Deployment certification

- Withdrawals

- Volunteer retention

- Attendance

- Conduct incidents

- Complaints resolved

- Volunteer satisfaction

- Safe return rate

Key risks

The Volunteer Director must monitor:

- Inadequate recruitment

- Excess volunteers

- Unqualified volunteers

- False credentials

- Incomplete screening

- Favoritism

- Training failure

- Payment misinformation

- Poor department placement

- Weak Team Leaders

- Volunteer burnout

- Harassment

- Retaliation

- Safeguarding violations

- Unauthorized travel

- Missing volunteers

- Privacy breaches

- Unmanaged family or child participation

- Poor accountability

- Last-minute withdrawals

- Deployment of someone on hold

Performance standards

The Volunteer Director will be evaluated on:

- Recruitment quality

- Application fairness

- Department staffing

- Screening completion

- Training completion

- Volunteer readiness

- Record accuracy

- Communication

- Retention

- Team Leader preparation

- Conduct management

- Complaint handling

- Volunteer welfare

- Accountability

- Successful final return and release

Immediate first 30-day action plan

The Volunteer Director should immediately:

- Meet with the Executive Director and Mission Director.

- Review the Master Operations Handbook.

- Establish the Volunteer Department structure.

- Draft department job descriptions.

- Finalize the volunteer lifecycle.

- Review registration and application forms.

- Establish application-review standards.

- Establish screening requirements.

- Establish department-placement procedures.

- Confirm the Each One, Reach One workflow.

- Create 100-, 150-, and 200-volunteer staffing scenarios.

- Develop the training and certification plan.

- Create the Volunteer Communications Calendar.

- Develop the Team Leader selection process.

- Create the Volunteer Readiness Dashboard requirements.

- Prepare the preliminary budget.

- Establish monthly reporting.

- Present a 90-day action plan to executive leadership.

The Volunteer Director remains responsible through January 3, 2029, for recruiting, screening, placing, training, certifying, supervising, supporting, and accounting for every UnityReach Global volunteer—from their first registration and referral through their final safe return and release in Fort Lauderdale.